## Template
Change management communication plan · template from fk-sd.de (Juliane Winterscheid, Fabian Kramer)
Week (relative to go-live) | Audience | Purpose (ADKAR) | Message | Sender | Channel | Owner | Feedback channel | Done

## Example CRM
Example: communication plan for a CRM rollout
Week (relative to go-live) | Audience | Purpose (ADKAR) | Message | Sender | Channel | Owner | Feedback channel | Done
-12 | Everyone in sales | Awareness | Why we introduce one shared CRM and what happens otherwise | Managing director | Town hall | Change manager | Questions in the town hall, shared mailbox
-11 | Sales managers | Desire | Your role, your questions, your messages for the team | Sponsor | Briefing | Change manager | Briefing
-10 | Field sales | Awareness | What changes for visit reports and forecasts | Regional head of sales | Regional meeting | Change manager | Regional key user
-8 | Works council | Awareness | Which reports the system allows and which it does not | Sponsor | Meeting | Project manager | Meeting
-4 | Inside sales | Knowledge | New quoting process, training dates | Project team | Email and intranet | Project manager | Key users
-2 | Everyone affected | Knowledge | What happens on go-live day, whom to ask | Key users | Team meeting | Change manager | Key users
+2 | Everyone affected | Reinforcement | First successes, most frequent questions, what we improve | Head of sales | Team meeting and email | Change manager | Shared mailbox