## Template
Stakeholder analysis · template from fk-sd.de (Juliane Winterscheid, Fabian Kramer)
Group or person | What changes in daily work? | Impact (1 to 3) | Influence (1 to 3) | Attitude today | ADKAR stage | Action | Owner | Date

## Example CRM
Example: stakeholder analysis for a CRM rollout
Group or person | What changes in daily work? | Impact (1 to 3) | Influence (1 to 3) | Attitude today | ADKAR stage | Action | Owner | Date
Head of sales | Forecasts come from the CRM instead of spreadsheets | 2 | 3 | supportive | Reinforcement | Make visible as sponsor, forecast in the monthly report from the system | Project manager
Field sales | Visit reports and opportunities in the CRM instead of their own spreadsheet | 3 | 2 | sceptical | Awareness | Show the benefit in their own day, key user per region | Head of sales
Inside sales | Quotes in the system instead of Word | 3 | 1 | open | Knowledge | Training on real cases, early testing | Change manager
Works council | New reporting options in the system | 1 | 3 | unknown | Awareness | Meeting in the first month, disclose reports | Sponsor
IT operations | Running and supporting the new system | 2 | 2 | supportive | Ability | Plan the handover to operations | Head of IT
Finance | New reports from the CRM | 1 | 2 | neutral | Awareness | Inform about new reports | Project manager